## AeroSphere Tracker
Phase | Module | Milestone | Status | Git Commit | Notes
0 | Planning & Architecture | Requirements & Scope | Completed
0 | Planning & Architecture | HLD | Completed
0 | Planning & Architecture | LLD | Completed
0 | Planning & Architecture | ADR | Completed
0 | Planning & Architecture | Database Design | Completed
0 | Planning & Architecture | API Design | Completed
1 | Foundation | Environment Setup | Completed | Initial foundation
2 | Common Module | ApiResponse | Completed
2 | Common Module | BaseEntity | Completed
2 | Common Module | ApplicationConstants | Completed
2 | Exception Module | Custom Exceptions | Completed
2 | Exception Module | GlobalExceptionHandler | Completed
2 | Configuration | OpenApiConfig | Completed
2 | Configuration | SecurityConfig | Completed | feat: implement common infrastructure, exception handling and application configuration
3 | Authentication | Authentication Module | Not Started |  | Current Phase
4 | Airport | Airport Module | Not Started
5 | Airline | Airline Module | Not Started
6 | Aircraft | Aircraft Module | Not Started
7 | Flight | Flight Module | Not Started
8 | Booking | Booking Module | Not Started
9 | Ticket | Ticket Module | Not Started
10 | Passenger | Passenger Module | Not Started
11 | Check-in | Check-in Module | Not Started
12 | Frontend | Frontend | Not Started
13 | Testing | JUnit 5 | Not Started
13 | Testing | Mockito | Not Started
13 | Testing | Integration Testing | Not Started
14 | Deployment | Docker & Production | Not Started
15 | Documentation | Phase Documents | In Progress |  | Create after each phase
15 | Documentation | Developer Handbook | Not Started |  | Final deliverable
15 | Documentation | MASTER_PROJECT_STATUS.md | Not Started |  | Update after each milestone
add secrets to the env before deploying